## Slide 1: Peer Advisor & Implementing Entity Workshop Session 1: Reflections on the process of moving from SOFF Readiness to Investment Phase
9 – 10 October 2024

## Slide 2: Readiness phase Positive aspects
Partnership and collaboration
Ground truthing
Knowledge transfer

## Slide 3: Readiness phase Challenging aspects
Tight timelines
Responsiveness
Logistics

## Slide 4: Readiness phase Lessons learned
Timing matters
Capacity building is not “one-size-fits-all”
Speaking the same language

## Slide 5: Readiness outputs for the development of SOFF Funding Request
The outputs of the Readiness phase are a unique resource for IEs and provide the basis for the design of the SOFF Funding request
Peer advisors can include additional information/needs beyond GBON, but must be included as an annex
The CHD provides a baseline for investments beyond SOFF – plan to repeat CHD assessment at end of Investment phase

## Slide 6: Challenges is using Readiness outputs in FR design
Length and technical nature of Readiness outputs can be challenging for IEs and non-experts to use
Technical “jargon” is not always understood in development context
For some topics, there are a range of possible options (e.g. calibration options) and these options should be explored and analyzed to identify best solution for each country
Ensure assessment of human and institutional capacity are specific to country circumstance
Costing of investments is not a requirement of the NCP, but is often helpful and used in the FR
CHDs are not always referred to in the FRs

## Slide 7: What we could do better?
How could the Readiness outputs be more useful for the design of SOFF Funding Requests?
Are there ways that we could facilitate between exchange between peer and IEs in the development of SOFF Funding Requests?
What could peer advisors do differently in the Readiness phase that may ease the development of FRs?

## Slide 8: Thank you

## Slide 9: Areas for improvement for Readiness
General
Inclusion of relevant experts on specific topics from peer advisor during the development of readiness phase outputs
Peer advisors propose solutions based on own experience – sharing and learning needed to understand all proposed solutions
Need to prepare cost:benefit assessment of different options per country – for example on calibration

## Slide 10: Areas for implement in Readiness output design
National Gap Analysis
Include coordinates for the newly installed stations, even if they are still tentative
Ensure alignment of the proposed improved stations with metadata stations in OSCAR/Surface. This is critical for our SOFF-funded stations database, as sometimes more than one station shares the same name
Ensure the affiliation of improved stations to GBON, without waiting for the investment phase to begin
National Contribution Plan
Assess the effectiveness and efficiency of various options for calibration: through the National Metrology Institution, Calibration Lab operated by NMHS, and Regional Instrument Centres
Comprehensive assesment on the other ongoing projects/initiatives, particularly for those related to meteorological observations and data exchanges
Coordinated technical trainings with other neighboring SOFF countries, where possible